ID Task Name Duration

0 **Project 314.5 days**

# Protocol Draft Finalization 4 days

1. CMP Animal Protocol Draft Finalization 4 days

# Animal Testing 120 days

1. **Wired Testing 8 days**
2. Alt. Current Wired for 6.0 Tube 4 days
3. Sim Man Testing Complete 4 days

# CMP Testing 60 days

1. Order more CMP prototypes 4 wks
2. CMP‐Wired Constructuion 2 wks

'12 Mar 4, '12 Apr 8, '12 May 13, '12 Jun 17, '12 Jul 22, '12 Aug 26, '12 Sep 30, '12 Nov 4, '12 Dec 9, '12 Jan 13, '13 Feb 17, '13 Mar 24, '13 Apr 28, '13 Jun 2, '13 S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W

1. Animal Testing ‐ Wired‐ Complete with CMP

30 days

# R & D 30 days

1. Design for Manufacturability 30 days
2. User Interface 30 days
3. Sourcing 30 days

# Animal Testing 2 60 days

1. Round 2 Protocol Finalization 1 wk
2. CMP Wireless Animal Testing 30 days

# Prepare IDE 104.5 days

1. IDE Preparation 100 hrs
2. IDE Submission 1 day
3. IDE Review Time 90 days
4. Approval 1 day

# IRB Submission 13.5 days

1. IRB Preparation 100 hrs
2. IRB Submission 1 day

# FDA Submission 194.5 days

1. 510k Preparation 100 hrs
2. 510k Packet Submission to FDA 1 day
3. FDA Review Time 180 days
4. FDA Market Approval 1 day

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Task | Project Summary | Inactive Milestone | Manual Summary Rollup | Deadline |
|  | SplitMilestone | External TasksExternal Milestone | Inactive SummaryManual Task | Manual SummaryStart‐only | Progress |
|  | Summary | Inactive Task | Duration‐only | Finish‐only |  |

Page 1

